## PMF
| Capgemini India Pvt. Ltd. | [8 empty] | Process to Know ( RACI and SLA)
[10 empty] | SI | Project Movement Steps | ICRES Space Team | Project Manager | Project SPOC | PMG SPOC | Group IT Network Engineer | Group IT Network Manager | Client | SLA (Business Day)
Project Movement | [9 empty] | 1 | Send PMF to project manager | R, A | C,I | I |  |  |  |  | 1
[10 empty] | 2 | Project Movement Form filled and submitted to ICRES Space Management by Project Manager. | I | A, C | R |  |  |  |  | 3
| Project Name | INI03_BD_USA_SOG |  |  | Old Location | KOL/KOL2/3FWINGC | Asset Information |  |  | 3 | Project Movement Form to be submitted to Group IT PMG Member | R, A | I | I | I | I |  |  | 1
| Project Code | 100000049 |  |  | New Location | KOL/KOL2/3FWINGC | Desktop | YES |  | 4 | Feasibility check and connectivity option / solution will be provided to Project manager | I | I,C | I,C | I | R,A | I |  | 2
| Discipline | [5 empty] | Laptop |  |  | 5 | Preparation & submission of change Document for Project Movement |  |  |  | I | R,A | I |  | 1
| Business Unit |  |  |  | Date | 2019-06-19 | No Machines |  |  | 6 | Review & Approval of Change request documents of Project Movement. |  |  |  |  | R | A
| SBU as per new Organization |  |  |  | Extension No. | 201989 | VOIP |  |  | 7 | Configuration of Devices at India End . (For Shifting of current Vlan & creating New Vlan) |  | I | I | I | R,A | C
| Project Manager |  |  |  | PM Mobile Number | 123456789 | Printer |  |  | 8 | Change Request to be raised with Group if Required |  |  |  |  | R,A | C |  | 1
| Project SPOC |  |  |  | Project SPOC Mobile Number | 123456789 | AV ( VC, Display screen etc) |  |  | 9 | Configuration of devices at Client /Capmini Group |  |  |  |  | R,A | C | R | SLA as per client
[10 empty] | 10 | Testing of Connectivity (UAT) and Confirmations | I | I | R,A | I | R | C | I | 1
[10 empty] | 11 | Movement of desktop/Laptop/Phone/LCD/Screen/Flex/whiteboards etc. | R,A | C,I | R,I | I | C | I |  | 1
[10 empty] | 12 | Project Movement ActivityDocumented at central repository |  |  |  | I | R,A | I |  | 1
To Be Filled by Project Manager
Total number of Project users at Old Location = |  |  |  | 2 |  | Working Hours | Start of Business | Close of Business
Number of users will be moving to new location = |  |  |  | 2 |  | Normal_Business_Hours | 11:00 | 20:30
Is this Partial Movement ? = YES / NO |  |  |  | NO |  | Working Days | Monday | Friday
Client Destination IP addresses |  |  |  | 100.00.00.0
Sr. No | Employee Name | Employee ID | User ID | Designation | Existing LAN IP Address from Project ODC Network ( Provide LAN IP after connecting via wired network) |  |  | Existing Cubicle No | New Cubicle No | Admin Rights (Yes / No) | Project Specific Software Requirements |  | PD port requried (Yes / No) | Laptop Desktop | VoIP |  |  | Monitor |  | CPU |  | Keyboard |  | Mouse
|  | Employee ID | [12 empty] | No | Serial No | Extension No | Make | Serial No | Make | Serial No | Make | Serial No | Make | Serial No
| Project Servers Name | Server Location | Existing IP address |  | Monitor |  | CPU |  | Keyboard |  | Mouse
[5 empty] | Make | Serial No | Make | Serial No | Make | Serial No | Make | Serial No
Any other project specific requirements/comments
1
2
3
Note on C11: basomu: Project person responsible for UAT coordination with Group IT & space management team
Note on I11: basomu: This equipments should be dedicated to project
Note on G23: basomu: No Wi-Fi IP address should be shared here
Note on L23: basomu: If yes, please share approval communications
Note on M23: basomu: Software license approval or client license referance to be provided
Note on O23: basomu: If yes, please share no. of PD enabled details in extising location

## RACI (hidden)
SI | Project Movement Steps | ICRES Space Team | Project Manager | Project SPOC | PMG SPOC | Group IT Network Engineer | Group IT Network Manager | Client | SLA (Business Day)
1 | Send PMF to project manager | R, A | C,I | I |  |  |  |  | 1
2 | Project Movement Form filled and submitted to ICRES Space Management by Project Manager. | I | A, C | R |  |  |  |  | 3
3 | Project Movement Form to be submitted to Group IT PMG Member | R, A | I | I | I | I |  |  | 1
4 | Feasibility check and connectivity option / solution will be provided to Project manager | I | I,C | I,C | I | R,A | I |  | 2
5 | Preparation & submission of change Document for Project Movement |  |  |  | I | R,A | I |  | 1
6 | Review & Approval of Change request documents of Project Movement. |  |  |  |  | R | A
7 | Configuration of Devices at India End . (For Shifting of current Vlan & creating New Vlan) |  | I | I | I | R,A | C
8 | Change Request to be raised with Group if Required |  |  |  |  | R,A | C |  | 1
9 | Configuration of devices at Client /Capmini Group |  |  |  |  | R,A | C | R | SLA as per client
10 | Testing of Connectivity (UAT) and Confirmations | I | I | R,A | I | R | C | I | 1
11 | Movement of desktop/Laptop/Phone/LCD/Screen/Flex/whiteboards etc. | R,A | C,I | R,I | I | C | I |  | 1
12 | Project Movement ActivityDocumented at central repository |  |  |  | I | R,A | I |  | 1

## List
Choose… | Normal_Business_Hours | H24_x_D5 | H24_x_D7 | Column1 | Days_1 | Days_2
Select | Select | Select | Select | Select.. | Start Day | Closing Day
Normal_Business_Hours | 0:00 | 0:00 | NA |  | Sunday | Sunday
H24_x_D5 | 0:30 | 0:30 |  |  | Monday | Monday
H24_x_D7 | 1:00 | 1:00 |  |  | Tuesday | Tuesday
| 1:30 | 1:30 |  |  | Wednesday | Wednesday
| 2:00 | 2:00 |  |  | Thursday | Thursday
| 2:30 | 2:30 |  |  | Friday | Friday
| 3:00 | 3:00 |  |  | Saturday | Saturday
| 3:30 | 3:30
| 4:00 | 4:00
| 4:30 | 4:30
| 5:00 | 5:00
| 5:30 | 5:30
| 6:00 | 6:00
| 6:30 | 6:30
| 7:00 | 7:00
| 7:30 | 7:30
| 8:00 | 8:00
| 8:30 | 8:30
| 9:00 | 9:00
| 9:30 | 9:30
| 10:00 | 10:00
| 10:30 | 10:30
| 11:00 | 11:00
| 11:30 | 11:30
| 12:00 | 12:00
| 12:30 | 12:30
| 13:00 | 13:00
| 13:30 | 13:30
| 14:00 | 14:00
| 14:30 | 14:30
| 15:00 | 15:00
| 15:30 | 15:30
| 16:00 | 16:00
| 16:30 | 16:30
| 17:00 | 17:00
| 17:30 | 17:30
| 18:00 | 18:00
| 18:30 | 18:30
| 19:00 | 19:00
| 19:30 | 19:30
| 20:00 | 20:00
| 20:30 | 20:30
| 21:00 | 21:00
| 21:30 | 21:30
| 22:00 | 22:00
| 22:30 | 22:30
| 23:00 | 23:00
| 23:30 | 23:30